## WIP Schedule
Work-in-Progress Schedule
GAAP percentage-of-completion, cost-to-cost method
Company: | Sample Contractor, LLC
Period ended: | 28-Feb-2026
Effective tax rate: | 0% | <- gross-up divisor; leave at 0% for a book-basis schedule
ILLUSTRATIVE SAMPLE - figures are fictional and do not represent any client.
Job Name | Target Margin | Final Contract | Current Budget (Est. Cost) | Billed to Date | Cost to Date | % Complete | Earned Revenue | Over / (Under) Billing | Gross Profit | Gross Margin | Status
Northside Distribution Centre - Shell |  | 879500 | 605600 | 629000 | 529835
Cedar Creek Equipment Barn |  | 736800 | 506600 | 736800 | 506600
Maple Ridge Horse Barn |  | 145900 | 99000 | 140100 | 77112
Riverbend Commercial Garage |  | 88100 | 64600 | 88100 | 55164
Westland Feedyard - Feed Shed |  | 96600 | 67300 | 77000 | 56678
Ironwood Shop Building |  | 201900 | 137000 | 182100 | 75627
Stonebridge Shop - Phase 1 |  | 96400 | 65500 | 30000 | 26914
Fairview Garage |  | 77200 | 52400 | 12000 | 3205
Lakemont Residence |  | 198000 | 134400 | 30000 | 4593
Brookhaven Machine Shed |  | 32900 | 20000 | 12000 | 9994
Trinity Community Centre |  | 165000 | 146300 | 111500 | 77957
Greenfield Hay Storage |  | 130000 | 88200 | 5000 | 6399
Prairie View Agricultural Building |  | 517300 | 350400 | 78000 | 14012
Kestrel Ridge Residence |  | 227800 | 154100 | 4000 | 4378
Total - all open jobs
Summary
Total contract value
Total estimated cost
Total billed to date
Total cost to date
Portfolio % complete (cost-to-cost)
Total earned revenue
Net over / (under) billing
Backlog (contract not yet billed)
Gross margin
Balance sheet presentation
Costs in excess of billings (asset) |  | underbilled jobs - revenue earned, not yet invoiced
Billings in excess of costs (liability) |  | overbilled jobs - invoiced ahead of work performed
Net position |  | agrees to total column J
How each column is calculated
Target Margin | (Final Contract - Current Budget) / Final Contract. The margin the job was priced to deliver.
% Complete | Cost to Date / Current Budget. The cost-to-cost method: progress is measured by cost consumed, not by time elapsed or a site walk.
Earned Revenue | Final Contract x % Complete. The revenue GAAP says you have earned, regardless of what you have invoiced.
Over / (Under) Billing | Earned Revenue - Billed to Date. Negative means you have invoiced ahead of the work (a liability). Positive means you have earned revenue you have not yet billed (an asset).
Gross Profit | Final Contract - Current Budget, at the current estimate. Recalculated every month as the budget moves.
Backlog | Final Contract - Billed to Date across all jobs. The figure your surety and lender ask for first.
What this schedule is for
- The schedule is only as good as the Current Budget. A budget that has not been updated for known cost growth will overstate both % complete and profit - this is what produces margin fade at close-out.
- Under US GAAP, if a contract is expected to finish at a loss, the entire loss is recognised as soon as it is probable and estimable - it is not spread across the remaining job.
- Cost-to-cost assumes cost is incurred evenly with progress. Where large materials are delivered but not installed, exclude them from Cost to Date or the job will look further along than it is.
Blue figures are inputs. Everything else is calculated - change an input and the schedule recalculates.
Prepared by FinRise Advisors ¦ finriseadvisors.com ¦ Sample for illustration only